## Inspection Checklist
Ohio Department of Transportation, Division of Construction | [7 empty] | Y
Inspection Quality Checklist | [7 empty] | N
524 Drilled Shafts
Header Section |  |  |  |  | Number of Non-Conforming Attributes: | 0
Name: |  | Date Inspected: |  | AltID:
PLN: |  | ContID:
Item No: |  | Project No. (Part Code):
Item Desc:
Location:
Checklist Section
Inspected? | Attribute Inspected | Citation | Inspection Location / Station / Offset | Photo? | Comments / Observations / Measurements | Conforms? (Y / N)
General
| As Per Plan, Miscellaneous, and Special items. In addition to the requirements listed below, do the special “As Per Plan” characteristics conform to the contract documents? Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
| No applicable Attribute for the Pay Item is listed. Provide a comment describing what was inspected. | Plan |  |  | Required |  | 0
Materials / Contractor's Installation Plan | [6 empty] | 0
| Did Contractor submit installation plan at least 14 days prior constructing drilled shafts? | 524.03 |  |  |  |  | 0
| Did Contractor’s installation plan include all the required information, such as how they planned to excavate shafts within alignment, clean out the shafts, keep water out, place rebar cages, and place concrete? | 524.03 |  |  |  |  | 0
| Did Contractor’s installation plan contain a list of proposed equipment to be used such as cranes, drills, augers, bailing buckets, final cleaning equipment, de-sanding equipment, slurry pumps, tremies, concrete pumps, casings? | 524.03 |  |  |  |  | 0
| Did Contractor’s installation plan include procedures and the proposed equipment required to deal with the possible presence of and subsequent removal of underground obstructions within the hole excavations? | 524.03 |  |  |  |  | 0
| For wet construction, did Contractor’s installation plan describe how they would remove the casing while not disconnecting or breaking apart the tremie or pump hose and monitor the level of the top of the concrete and the bottom of the pump or tremie hose? | 524.03 |  |  |  |  | 0
| Did Contractor provide certified test data, mill certifications with proof of domestic origin, for permanent casing per 711.07? | 524.04.D / 524.06 |  |  |  |  | 0
| Did Contractor use epoxy coated reinforcing steel according to 509, and Class QC 4 for mass concrete , over 7 foot diameter shaft, or QC 5 according to 499? | 499/509.03 |  |  |  |  | 0
| Does the Concrete Job Mix Formula(JMF) supplied match the Engineer approved JMF? Document the approved JMF. | 499 / 524.02 / 1126 |  |  | Required |  | 0
| For Mass QC 5 Concrete, did Contractor submit a Thermal Control Plan(TCP) at least 10 days before mass concrete placement ? | 511.04 / 524.02 |  |  |  |  | 0
| For Mass QC 5 Concrete, TCP included procedures and equipment to monitor and control concrete temperature during placement and cure? | 511.04 / 524.02 |  |  |  |  | 0
| Was reinforcing steel properly stored and kept free of dirt? | 524.09 / 509.03 |  |  |  |  | 0
Construction | [6 empty] | 0
| If the excavation included bedrock, was the elevation where bedrock encountered documented for determination of length of drilled shafts above and below the bedrock? | 524.16 |  |  |  |  | 0
| If obstructions were encountered during the shaft excavation, was the method and time to remove the number and size of the obstructions documented on the CA-S-1 form? | 524.16 |  |  |  |  | 0
| If the dry method was used, were the sides stable and any flow of water into the excavation less then 12 inches per hour? | 524.04 A |  |  |  |  | 0
| If wet construction method was used for a shaft which was not socketed into bedrock, was the water or slurry fluid level during the drilling operation, inside the drilled shaft, higher then the static water table? | 524.04 B |  |  |  |  | 0
| If temporary casing was used, was at least a 5 foot head of concrete maintained above the bottom of the casing as the casing was withdrawn? | 524.04 C |  |  |  |  | 0
| If temporary casing was used, was the casing extracted at a slow, uniform rate with the pull in line with the shaft, without deforming the reinforcing steel cage? | 524.04 C |  |  |  |  | 0
| If permanent casing was required, did the contractor excavate material beyond the limits of the casing? | 524.04 D |  |  |  |  | 0
| If permanent casing was required, did the contractor excavate a pilot hole no larger than one-half the diameter of the shaft ahead of the casing until the casing reaches the desired penetration? | 524.04 D |  |  |  |  | 0
| If permanent casing was required, did the contractor keep the casing continuous between the elevations shown on the plans? | 524.04 D |  |  |  |  | 0
| If permanent casing was required, did the contractor pressure grout voids between the shaft excavation and the casing with cement grout, after filling the permanent casing with concrete? | 524.04 D |  |  |  |  | 0
| If the drilled shaft was in open water, did the contractor keep the casing a minimum of 12 inches above the water? | 524.06 |  |  |  |  | 0
| If the shaft was a friction type, and if the concrete was not placed the same day that the excavation was completed, did the Contractor protect the excavation with a temporary casing, and redrill the hole at least 6 inches larger in diameter, clean the excavation, and perform slurry test before concreting? | 524.05 |  |  |  |  | 0
| If a slurry was used, was it sufficient to maintain the stability of the excavation and to allow proper concrete placement? Document type of slurry used. | 524.07 |  |  | Required |  | 0
| If a Polymer slurry was used, did the Contractor use it in a test hole to prove its ability to maintain the stability of the excavation? | 524.07 |  |  |  |  | 0
| If a mineral slurry was used, did the Contractor perform control tests using suitable apparatus to determine density, viscosity, and pH that conform to the values shown in Table 524.07-1? | 524.07 |  |  |  |  | 0
| Did the Contractor provide equipment for checking the dimensions and alignment of each shaft excavation? Document the dimensions and alignment and final depth. | 524.08 |  |  | Required |  | 0
| Immediately before placing rebar cage and concrete, did the Contractor check the bottom of the completed drilled shaft excavation for cleanliness and remove all drilling spoils? | 524.08 |  | Required |  |  | 0
| Were spacers attached to the reinforcing cage at quarter points and spaced at intervals not to exceed 5 feet along the length of the cage? | 524.09 |  | Required |  |  | 0
| Were round spacers of the proper size used to maintain the required clearance, ie.3 inches for shaft diameters up to 4 feet and 6 inches for shaft diameters larger than 4 feet ? | 524.09 |  |  |  |  | 0
| Did the water-cement ratio not exceed 0.44 and if concrete was placed underwater, 10 cement added to the mix? | 524.10. |  |  |  |  | 0
| If concrete was placed underwater, was it placed in one continuous operation? | 524.10. |  |  |  |  | 0
| If concrete was placed underwater, was concrete pumped above the top of the shaft to remove contaminated concrete (laitance)? | 524.10. |  | Required |  |  | 0
| If a pump was used to place concrete underwater, was the end of the pump maintained at least 10 feet below the surface of the fresh concrete? | 524.13 |  | Required |  |  | 0
| If a tremie was used to place concrete underwater, was the end of the 10 inch minimum diameter tremie maintained at least 10 feet below the surface of the concrete? | 524.12 |  |  |  |  | 0
| If a pump or tremie was used to place concrete under water, was the end of the pump or tremie properly plugged when it was placed into the water? | 524.12 / 524.13 |  |  |  |  | 0
| If drilled shaft hole excavation was dry, did the Contractor use the free fall method with a 3 foot long centering drop chute and not strike the sides of the excavation, casing or rebar cage when placing concrete? | 524.11 |  |  |  |  | 0
| For shafts supporting single columns, were the drilled shaft within 3 inches of the plan location in the horizontal plane at the plan elevation for the top of the shaft? Document position of shaft. | 524.14 |  | Required | Required |  | 0
| For shafts supporting footings, were the drilled shaft within 6 inches of the plan location in the horizontal plane at the plan elevation for the top of the shaft? Document position of shaft. | 524.14 |  | Required | Required |  | 0
| Was the Drilled Shaft's vertical alignment within 1/4 inch per foot of depth? | 524.14 |  |  |  |  | 0
| Completed Form CA-S-1, Inspection Record for Drilled Shafts? | MOP |  |  |  |  | 0
Comments Section
Inspection Guidance / Instruction Section
Provide comments for each nonconformance.
This Checklist should be filled out for each structure with drilled shafts installed on the project.